## Ark1
"Lofthus frukt og saft" website | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5
| M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
Dato | 2019-01-01 | 2019-01-02 | 2019-01-03 | 2019-01-04 | 2019-01-05 | 2019-01-06 | 2019-01-07 | 2019-01-08 | 2019-01-09 | 2019-01-10 | 2019-01-11 | 2019-01-12 | 2019-01-13 | 2019-01-14 | 2019-01-15 | 2019-01-16 | 2019-01-17 | 2019-01-18 | 2019-01-19 | 2019-01-20 | 2019-01-21 | 2019-01-22 | 2019-01-23 | 2019-01-24 | 2019-01-25 | 2019-01-26 | 2019-01-27 | 2019-01-28 | 2019-01-29 | 2019-01-30 | 2019-01-31
TASK
Project Management | bar: WEEK 1 M to WEEK 5 W
STARTUP AND PLANING PHASE | WEEK 1 M: Startup project
Client meeting/workshop new website | bar: WEEK 1 M to WEEK 1 T
Project planning | bar: WEEK 1 W to WEEK 1 TH
Reseach project startup | bar: WEEK 1 F to WEEK 1 SA
WEB CONTENT NAD TEXT | WEEK 1 SU: Milestone
Copy of draft | bar: WEEK 1 SU to WEEK 2 M
Copy final | bar: WEEK 2 T to WEEK 2 W
DESIGNPHASE | WEEK 2 TH: Milestone
Reseach design | bar: WEEK 2 TH to WEEK 2 F
Style tyle | bar: WEEK 2 SA to WEEK 2 SU
Layout/web sketches | bar: WEEK 3 M to WEEK 3 W
Adobe XD/Prototype | bar: WEEK 3 TH to WEEK 3 F
Propose deisng | bar: WEEK 3 SA
Final Design | bar: WEEK 3 SU
PHOTO
Take pictures | bar: WEEK 1 SU to WEEK 2 M
Post-production | bar: WEEK 2 T to WEEK 2 W
DEVELOPMENT | WEEK 4 M: Milestone
Front-End Dev | bar: WEEK 4 M to WEEK 4 SU
Back-End Dev | bar: WEEK 4 M to WEEK 4 SU
Propose site | bar: WEEK 5 M
Finalize | bar: WEEK 5 T
Launch | bar: WEEK 5 W
0
Activities | WEEK 1 M: Lead; WEEK 1 T: Start date; WEEK 1 W: Duration; WEEK 1 TH: End date; WEEK 1 F: Stauts %
Project management | WEEK 1 M: Project manager; WEEK 1 T: 2019-01-01; WEEK 1 W: 31; WEEK 1 TH: 2019-01-31; WEEK 1 F: Not started
STARTUP AND PLANING PHASE
Client meeting/workshop new website | WEEK 1 M: Project manager Copywriter. Back-end develper; WEEK 1 T: 2019-01-01; WEEK 1 W: 2; WEEK 1 TH: 2019-01-02; WEEK 1 F: Not started
Project planning | WEEK 1 M: Project manager; WEEK 1 T: 2019-01-03; WEEK 1 W: 2; WEEK 1 TH: 2019-01-04; WEEK 1 F: Not started
Reseach project startup | WEEK 1 M: Project manager Copywriter. Back-end develper; WEEK 1 T: 2019-01-05; WEEK 1 W: 2; WEEK 1 TH: 2019-01-06; WEEK 1 F: Not started
WEB CONTENT NAD TEXT
Copy of draft | WEEK 1 M: Copywriter; WEEK 1 T: 2019-01-07; WEEK 1 W: 2; WEEK 1 TH: 2019-01-08; WEEK 1 F: Not started
Copy final | WEEK 1 M: Copywriter; WEEK 1 T: 2019-01-09; WEEK 1 W: 2; WEEK 1 TH: 2019-01-10; WEEK 1 F: Not started
DESIGNPHASE | WEEK 1 F: Not started
Reseach design | WEEK 1 M: Visual designer; WEEK 1 T: 2019-01-11; WEEK 1 W: 2; WEEK 1 TH: 2019-01-12; WEEK 1 F: Not started
Style tyle | WEEK 1 M: Visual designer; WEEK 1 T: 2019-01-13; WEEK 1 W: 2; WEEK 1 TH: 2019-01-14; WEEK 1 F: Not started
Layout/web sketches | WEEK 1 M: Visual designer; WEEK 1 T: 2019-01-15; WEEK 1 W: 3; WEEK 1 TH: 2019-01-17; WEEK 1 F: Not started
Adobe XD/Prototype | WEEK 1 M: Visual designer; WEEK 1 T: 2019-01-18; WEEK 1 W: 2; WEEK 1 TH: 2019-01-19; WEEK 1 F: Not started
Propose deisng | WEEK 1 M: Project manager; WEEK 1 T: 2019-01-20; WEEK 1 W: 1; WEEK 1 TH: 2019-01-20; WEEK 1 F: Not started
Final Design | WEEK 1 M: Visual Designer; WEEK 1 T: 2019-01-21; WEEK 1 W: 1; WEEK 1 TH: 2019-01-21; WEEK 1 F: Not started
PHOTO
Take pictures | WEEK 1 M: Freelance photographer; WEEK 1 T: 2019-01-07; WEEK 1 W: 2; WEEK 1 TH: 2019-01-08; WEEK 1 F: Not started
Post-production | WEEK 1 M: Freelance photographer; WEEK 1 T: 2019-01-09; WEEK 1 W: 2; WEEK 1 TH: 2019-01-10; WEEK 1 F: Not started
DEVELOPMENT
Front-End Dev | WEEK 1 M: Front-End Developer; WEEK 1 T: 2019-01-22; WEEK 1 W: 7; WEEK 1 TH: 2019-01-28; WEEK 1 F: Not started
Back-End Dev | WEEK 1 M: Back-End Developer; WEEK 1 T: 2019-01-22; WEEK 1 W: 7; WEEK 1 TH: 2019-01-28; WEEK 1 F: Not started
Propose site | WEEK 1 M: Project manager; WEEK 1 T: 2019-01-29; WEEK 1 W: 1; WEEK 1 TH: 2019-01-29; WEEK 1 F: Not started
Finalize | WEEK 1 M: Front/Back-End Deloper; WEEK 1 T: 2019-01-30; WEEK 1 W: 1; WEEK 1 TH: 2019-01-30; WEEK 1 F: Not started
Launch | WEEK 1 M: Project manager Back-end develper; WEEK 1 T: 2019-01-31; WEEK 1 W: 1; WEEK 1 TH: 2019-01-31; WEEK 1 F: Not started